LGT Reporting Warehouse — Work Plan Summary (v1.1, 2026-09-22)

Full document: LGT-PBIP-Reports/warehouse-analysis/LGT Reporting Warehouse Work Plan.docx (audience: Jake).

Roles

- Jake (LGT) does the build: SQL/DDL in the sqlproj, loads, Power BI model rebuilds, publishing from the LGT-VMW2 VM.

- Eric (EDD) consults: design decisions, review of each phase's DDL and tie-out results, pairing on the hard pieces (WIP fact, CAS migration). Anything Eric drafts on the laptop is deployed and verified by Jake on the VM via the GitHub sync loop.

Situation

- Five PBIP models (3 Year Billing, Annual Review, Timesheet Review, CAS Management, New Business Report), all importing from production lgt on lgt-pm03\practicemgt. Annual Review ⊂ Timesheet Review.

- Two warehouse designs exist and diverge: Eric's draft DDL in warehouse-analysis/sql (ref/dim/fact/rpt/usp, PascalCase) vs. Jake's lgt-reporting-db sqlproj scaffold (staging/dim/fact, snake_case; Clients/Staff staging, dim_client, dim_client_group, dim_employee, fact_engagement; structure only).

Plan (phases, est. hours Jake / Eric)

- Reconcile designs into the sqlproj, verify source column names — 6-8 / 2-3

- ref.* + dim.Date + conformed dims — 12-16 / 4-6

- fact.WipTransaction + fact.Invoice + fact.ArTransaction + billing tie-out for one closed year — 16-24 / 4-6 (milestone: billing partner sign-off)

- Timesheet Review on rpt views; retire Annual Review — 10-14 / 3-4

- Rebuild 3 Year Billing on rpt.Billing / usp.Rpt_BillingSummary / usp.Rpt_LostClients — 8-12 / 2-3

- Migrate CAS Management (fix SkDesc rank bug, replace GETDATE windows with @AsOfDate) — 24-32 / 6-8

- Migrate New Business (dim.ClientGroup, usp.Rpt_ClientGroupSummary) — 10-14 / 3-4

- Cutover: Agent job, ETL log, remove prod credentials — 8-12 / 4-6 Total ≈ 95-130 h Jake, 28-40 h Eric. Phases 3, 4, 6 independent once Phase 2 is accepted; Phase 5 last.

Decisions pending (owner)

1 canonical Amount Invoiced (WIP-derived vs Invoice table); 2 realization formula; 3 hours bucket rule; 4 week start (Mon recommended); 5 include inactive employees (yes); 6 exclude PII (yes); 7 skill tier map + which Emprate# is standard/non-bill (Jake, blocks dim.Employee); 8 fiscal year Oct-Sep firm-wide?; 9 warehouse = lgt_reporting (done); 10 adopt draft naming in sqlproj (Phase 0).

Conformed billing columns (fact.WipTransaction)

InvoicedAmount = billable & H,P → Wfee+Wwrupdn+Wexp+Wsurchg (Wipdate); ProductionAmount = billable & W,H → Wfee+Wsurchg (Wdate); GrossWipAmount = billable & W → Wfee+Wexp; BilledStandardAmount = H → Wbilled; BilledActualAmount = H,P → Wbilled+Wwrupdn; WriteUpDownAmount = H → Wwrupdn; BilledHours = H → Whours; WorkedHours = billable & W,H → Whours; HoursBucket: Billable = WType 0 & Wbillable 1, PTO = 1,2,4,5, Other = 3, Marketing = 6.

Billing tie-out (Phase 2 gate)

Five tests vs. current reports for one closed year (2025) + YTD: (1) rpt.Billing by partner/month vs 3YB [Billings]/[Adj]/[Hrs] — must match to the cent; (2) vs CAS BR Total Invoiced; (3) ProductionAmount vs 3YB [Fee Amount] and CAS Gross WIP — known surcharge/expense difference; (4) WIP-derived vs fact.Invoice by client — variance quantifies Decision 1; (5) HoursBucket vs Timesheet Bucket/HourGroup — differences only on WType 1,4,5.

Changelog

- v1.1 (2026-09-22): hours swapped — Jake builds, Eric consults. Roles paragraph and risk table reworded to match.

- v1.0 (2026-09-17): initial draft.