Lane Gorman Trubitt

Reporting Warehouse: Consolidation & Standardization Work Plan

Moving the five Power BI reports off the production Practice Management database and onto one governed reporting layer

Prepared for: Jake, Lane Gorman Trubitt

Prepared by: Eric Nichols, Eric Does Data LLC

Date: September 17, 2026

Version: 1.0 (draft for review)

Repositories referenced: LGT-PBIP-Reports (five PBIP models and the warehouse-analysis draft), lgt-reporting-db (SQL Database Project for lgt_reporting on LGT-VMW2)

# 1. Purpose and current state

LGT currently runs five Power BI reports, each with its own semantic model that imports directly from the production Practice Management database (lgt on lgt-pm03\practicemgt). Every model re-implements the same joins, filters, and business rules in its own mix of native SQL, Power Query (M), and DAX. The result is that "billings," "fees," "hours," "week," and "client" each mean something slightly different depending on which report you open, and every refresh puts load on the production server.

The reporting warehouse (lgt_reporting on LGT-VMW2) changes that. Production is touched only by simple, scheduled ETL jobs that copy the source tables over. Everything else, including the derived measures, calendars, and reference data, lives in the warehouse and is defined exactly once. Each Power BI report then imports from a small set of standardized views instead of raw tables.

This document is the work plan for getting there. It is scoped to the five reports in the repository today and focuses on the specific tables, columns, and rows that need to be consolidated so that billing figures tie across every report, and so the 3 Year Billing report in particular can be rebuilt on a clean, reusable base.

## 1.1 Where things stand

- Five PBIP models in source control. 3 Year Billing, Annual Review, Timesheet Review, CAS Management, New Business Report. Annual Review and Timesheet Review are the same model (Timesheet Review is a superset with 13 more measures and an Unposted Time page); they should already be one dataset.

- A full draft warehouse design exists. The warehouse-analysis folder in the PBIP repo contains a common-objectives analysis and draft T-SQL for five schemas (ref, dim, fact, rpt, usp): 13 reference tables, 15 dimensions, 9 facts, 13 report views, 8 load procedures, and 7 parameterized report procedures. It has been parsed but not executed against a server.

- A narrower scaffold is already in the SQL Database Project. lgt-reporting-db has staging.Clients, staging.Staff, dim.dim_client_group, dim.dim_client, dim.dim_employee, and fact.fact_engagement: structure only, no load procedures, no date table, no WIP, invoice, or AR facts. Four columns in dim_employee are marked unresolved (SkillRank, StandardBillRate, NonBillRate, and the Department/SkillLevel lookups).

- The two designs do not yet agree. They use different schemas (staging/dim/fact vs. ref/dim/fact/rpt/usp), different naming (dim_client vs. dim.ClientEngagement), and different grain for the client dimension. Reconciling them is the first task in this plan, before any more tables are added to the project.

## 1.2 Why the current models are fragile

- Five separate definitions of amount invoiced, three of fees, three week-start conventions, and two conflicting PTO rules inside the same table (Annual/Timesheet Fact_WIP carries an M column Bucket and a DAX column HourGroup that disagree).

  - What is the week definition at LGT? Mon-Sun, Sun-Sat, etc?

- Reference data that should be maintained in a table is hardcoded in the models: a 456-row NAIC-to-Niche map, niche goals, skill rank tiers, position eligibility, status sort order, a 30-name retired-partner exclusion list, and the YTD cutoff month.

- Full-width imports of Clients (126 columns) and Employee (100 columns) into three models, including federal tax IDs and SSN fields that no visual uses.

- Rolling windows computed with GETDATE() inside native SQL (CAS capacity, forecast compliance, skill violations, New Business revenue windows), so nothing can be run as-of a prior date or reproduced later.

- A likely bug in CAS Management: the skill-rank CASE keyed on SkDesc expects "Staff", "Senior", "Manager", but the source values are "Staff I", "Senior II", "Super Senior", so most rows fall to rank 99.

- Four tables in 3 Year Billing (vpm9_AR_Invoices, vpm9_AR_Payments_by_Client, vpm9_AR_Payments_by_Master, vpm9_main_billing) plus Employee and SICCode are imported but referenced by no visual. They cost refresh time and add nothing.

# 2. Report inventory

What each model imports today, how it is built, and how much of it is actually used. Column and measure counts come from the TMDL definitions in the repo.

| Report | Source tables imported | How it is built | Measures | Pages |
| --- | --- | --- | --- | --- |
| 3 Year Billing | WIP + Clients (one native query), Clients (126 cols), Employee (100), Department, SICCode, vpm9_AR_Invoices, vpm9_AR_Payments_by_Client, vpm9_AR_Payments_by_Master, vpm9_main_billing, NAIC_Niche (hardcoded) | One SQL query computes AmountInvoiced, WIP Generated, HoursH, AdjH per WIP row; YTD/PYTD via DAX with a CutoffMonth slicer; partner exclusion list in a DAX column | 27 | Billing Summary, Billings by Partner, Billings by Niche, Lost Clients by Partner, Clients Breakdown |
| Annual Review | WIP, TimeEntry, EmpBudHRS, EmpCltBudget, SkillLevel, Clients (127), Employee (102), Department, ServiceCodes | Raw full-table imports; buckets and week-end added in M and DAX; 26 auto-date tables | 17 | Staff Hours vs. Goal, Time Drilldown |
| Timesheet Review | Same as Annual Review + LastRefresh | Identical model to Annual Review with additional measures | 30 | Time Sheet Review, Staff Hours vs. Goal, Unposted Time, Export, Time Drilldown |
| CAS Management | WIP, CltDue, CltBudget, CltDueRouting, EmpBudHRS, EmpCltBudget, EmpForecast, Invoice, Clients, Employee, Department, SkillLevel, ServiceCodes, WorkEntity, LineOfBusiness, TrackingStatus, ProjectPositions, DDEvents | 26 native SQL queries forming a proper star (10 dims, 10 facts, 5 SQL views); incremental refresh on fact_wip (RangeStart/RangeEnd); fiscal year Oct-Sep; several hardcoded DAX tables | 148 | Resource Mgmt, Project Mgmt, Capacity, Performance Review, Staff Forecast (kanban custom visual) |
| New Business Report | Clients (127), Employee (100), Department, LineOfBusiness, Invoice, AcctsRec | One large native query (vw_GroupSummary, one row per Engrelated group) plus a DAX re-implementation of it (GroupSummary_Final_); NicheTable and NicheGoals hardcoded | 8 | New Business Summary, By Department, Niche Tree |

Every model imports from the same single database. There are no other sources, which is what makes a single warehouse layer feasible.

# 3. What to consolidate: tables, columns, and rows

This section is the core of the plan. It lists, at the table and column level, what the warehouse needs to carry so the five reports can be rebuilt on it, and what should be left behind.

## 3.1 Source tables to bring over (and which rows)

These are the production tables the ETL jobs copy into staging. The "rows" column is the filter applied at load; everything else is left in production.

| Source table | Rows to load | Load pattern | Feeds |
| --- | --- | --- | --- |
| WIP | Windicator in (W, H, P). Exclude D (deleted/void). | Incremental on Wdstamp / LastUpdated; full reload option | fact.WipTransaction: every billing, production, hours, and WIP-balance measure |
| Clients | All rows, including Deleted = 1 (flagged), so historical WIP keeps its engagement | Truncate and reload | dim.ClientEngagement, dim.ClientGroup |
| Employee | All rows: active, inactive, and deleted (flagged). CAS currently filters Empstatus = A at source and loses departed staff. | Truncate and reload | dim.Employee |
| Department, SkillLevel, ServiceCodes, LineOfBusiness, TrackingStatus, ProjectPositions, DDEvents, WorkEntity, SICCode | All rows | Truncate and reload (small) | Small dimensions |
| TimeEntry | Only TEindicator <> R (unreleased). Released time is already in WIP. | Truncate and reload each run (small, volatile) | fact.TimeEntryUnreleased: Unposted Time page |
| EmpBudHRS | All rows (no Deleted column in source) | Truncate and reload | fact.EmployeeBudgetMonth |
| EmpCltBudget | All rows; no rolling window at load (CAS currently cuts at -12 weeks in SQL) | Truncate and reload | fact.EmployeeSchedule |
| EmpForecast | All rows, Deleted flagged | Truncate and reload | fact.EmployeeForecastWeek |
| CltDue, CltBudget, CltDueRouting | All rows, Deleted flagged where the column exists | Truncate and reload | dim.Project, fact.ProjectBudgetLine, fact.ProjectStatusLog |
| Invoice | One row per InvNumber. Source joins to Clients on Cltnum only and fans out; dedupe at load. | Truncate and reload | fact.Invoice |
| AcctsRec | ARStatus = P and ARVoid = 0. Finance charges (ARType 3) carry their amount in ARFin, not ARAmt. | Truncate and reload | fact.ArTransaction |

Do not bring over: the four vpm9_* views (unused by any visual; AR comes from AcctsRec instead), the full 126-column Clients and 100-column Employee imports, and the PII columns Engfedid, Engss1, Engss2, SSN, password hashes, phone and address fields. Nothing downstream uses them.

## 3.2 Conformed dimensions

One version of each dimension, replacing the copies that exist in each model today. The right-hand column is what changes for the reports.

| Warehouse table | Grain | Replaces | Key columns and rules |
| --- | --- | --- | --- |
| dim.Date | Day, 2015-2035 | Five calendars (3YB Date, Annual/Timesheet DimDate, CAS dim_date, New Business Date) plus ~75 auto-generated LocalDateTable objects | Carries both WeekStartMon/WeekEndSun and WeekStartSun/WeekEndSat so each report picks one column; FiscalYear (Oct start); YearMonthNum; IsCurrent flags computed in a view, not stored |
| dim.Employee | Employee.ID | Employee (3YB, NB), Dim_Employee (Annual, Timesheet), dim_employee (CAS), and staging.Staff/dim_employee in the sqlproj | All employees with IsActive and IsDeleted flags; both FullName and NameLastFirst; SkillRank/SkillTier from ref.SkillLevelTier; EmployeeNumberInt for CPPnum/CRPnum joins; StandardBillRate and NonBillRate sourced from the rate tier Jake confirms (Decision 7) |
| dim.ClientEngagement | Clients.ID (client + engagement) | Clients (3YB, NB), Dim_Clients (Annual, Timesheet), dim_client (CAS), fact_engagement in the sqlproj | About 40 curated columns, no tax IDs; GroupKey = Engrelated; IsPrimaryEngagement = CltEng = 0; status description from ref.ClientStatus; Niche via ref.NaicNiche; partner, manager, biller, originator IDs resolved to dim.Employee |
| dim.Client | Cltnum | dim_client in the sqlproj | Optional roll-up; bridge for Invoice/AR which key on Cltnum only. Which engagement supplies ClientName is Decision 10. |
| dim.ClientGroup | Engrelated | vw_GroupSummary and GroupSummary_Final_ (NB), dim_client_group in the sqlproj | GroupLabel priority: manual override > .0 engagement name > earliest active > key; primary department by plurality; CohortYear; IsUserNamed protects partner-curated names from reload. Revenue windows move to rpt.ClientGroupSummary because they depend on an as-of date. |
| dim.SkillLevel | SkillLevel.SkID | dim_skill_rank DATATABLE and three CASE blocks in CAS | SkillRank and SkillTier from ref.SkillLevelTier (21 rows). Fixes the SkDesc CASE bug. |
| dim.ServiceCode | ServiceCodes.ID | ServiceCodes (Annual, Timesheet), dim_service_code (CAS) | Category/sub/detail; TimeTypeCode and HoursBucket from ref.TimeType |
| dim.Department | DeptID | Five copies | Unchanged |
| dim.Project and the CAS project dims | CltDue.CDID etc. | CAS dim_project, dim_project_type, dim_project_position, dim_tracking_status, dim_work_type, dim_entity_type, dim_lob | Logic unchanged from the CAS native queries, moved into the warehouse. Health and DaysUntilDue are not stored; they come from usp.Rpt_ProjectHealth @AsOfDate. |

## 3.3 Conformed billing and production measures (the tie-out)

This is the standard that makes every billing report agree. Each amount is computed once, per WIP row, at load time in fact.WipTransaction. Reports sum the column; they do not re-derive it. Names map to what the reports call them today.

| Warehouse column | Rule (per WIP row) | Date basis | Replaces / today's label |
| --- | --- | --- | --- |
| InvoicedAmount | Wbillable = 1 and Windicator in (H, P): Wfee + Wwrupdn + Wexp + Wsurchg | InvoicePostDate (Wipdate) | 3YB "AmountInvoiced" / [Billings]; CAS "BR Total Invoiced" |
| ProductionAmount | Wbillable = 1 and Windicator in (W, H): Wfee + Wsurchg | WorkDate (Wdate) | 3YB "WIP Generated" / [Fee Amount] |
| GrossWipAmount | Wbillable = 1 and Windicator = W: Wfee + Wexp | WorkDate | CAS "Gross WIP" / "Project WIP $" |
| BilledStandardAmount | Windicator = H: Wbilled | InvoicePostDate | CAS "WIP At Standard" |
| BilledActualAmount | Windicator in (H, P): Wbilled + Wwrupdn | InvoicePostDate | CAS "Invoiced WIP" / "Gross Billings" |
| WriteUpDownAmount | Windicator = H: Wwrupdn (WriteDownAmount = ABS of negatives, WriteUpAmount = positives) | InvoicePostDate | 3YB "AdjH" / [Adj]; CAS "Write Up Down" |
| ProgressAmount | Wbillable = 1 and Windicator = P: Wfee | InvoicePostDate | CAS "WS Progress" (sign handled in the view) |
| BilledHours | Windicator = H: Whours | InvoicePostDate | 3YB "HoursH" / [Hrs] |
| WorkedHours | Wbillable = 1 and Windicator in (W, H): Whours | WorkDate | CAS "Total Actual Hours" |
| Hours | Whours, unfiltered | WorkDate | Annual/Timesheet "Total Hours" |
| HoursBucket | Billable = WType 0 and Wbillable 1; PTO = WType in (1, 2, 4, 5); Other = 3 (CPE); Marketing = 6; else NonBillable | WorkDate | Annual/Timesheet Bucket and HourGroup (conflicting); CAS TimeTypeDesc |
| LaborCost | Whours * Wcost | WorkDate | CAS cost measures |

Realization: two formulas exist. 3 Year Billing uses 1 + Adj / (Billings - Adj); CAS uses BilledActual / BilledStandard. They are close but diverge when expenses and surcharges are present. The warehouse exposes both numerators and denominators; the named measure "Realization %" in every report will use whichever formula is chosen in Decision 2.

Invoice table vs. WIP-derived billings: New Business uses Invoice.InvAmount + InvAdjust on InvDate; the other reports derive invoiced amounts from WIP rows on Wipdate. These will not tie exactly (progress bills, timing). The warehouse carries both (fact.WipTransaction.InvoicedAmount and fact.Invoice.NetBilledAmount) and the tie-out in section 6 quantifies the difference before a primary is chosen (Decision 1).

## 3.4 Reference data to move out of the models

Each of these is a hardcoded DATATABLE, embedded binary, or CASE expression today. They become small maintained tables in the ref schema so Jake or a partner can change them without republishing a report.

| ref table | Today | Rows / notes |
| --- | --- | --- |
| ref.NaicNiche | 3YB NAIC_Niche DATATABLE; NB NicheTable embedded binary | 456 rows; already extracted to 01b_ref_naic_niche.sql |
| ref.NicheGoal | NB NicheGoals DATATABLE | Made year-aware (GoalYear, ReportingNiche, GoalNiche, EstFeeGoal) |
| ref.SkillLevelTier | CAS dim_skill_rank + two CASE blocks | 21 rows, SkID to rank 1-5 and tier |
| ref.PositionSkillEligibility | CAS SkillRoleEligibility DATATABLE | 10 rows |
| ref.ProjectStatusSort | CAS StatusSortOrder | 12 rows, with HealthGroup |
| ref.WorkTypeLobGroup | CAS LOBGroup CASE (duplicated in dim_client and dim_work_type) | 4 rows |
| ref.TimeType | WType/SCType labels in three places | 7 rows, with the one HoursBucket rule |
| ref.WipIndicator, ref.ClientStatus | Implicit in filters everywhere | W/H/P/D and Engstatus 0-4 semantics |
| ref.PartnerExclusion | 3YB "CPPLname (groups)" DAX column, 30 names | Maintained list; dim.Employee.IsExcludedPartner |
| ref.ClientGroupLabelOverride | NB ManualGroupLabel (empty) | Partner-curated group names |
| ref.Setting | Constants in SQL and DAX | WeeksPerMonth 4.33, FiscalYearStartMonth 10, utilization bands, ProjectAtRiskDays 7, StandardWeekHours 40 |

## 3.5 Standardized report views

Power BI imports these and nothing else. One view per reporting objective; views never call GETDATE(). Anything that depends on an as-of date is a parameterized procedure.

| View / procedure | Objective | Replaces |
| --- | --- | --- |
| rpt.WipProduction | Production / time | Annual/Timesheet Fact_WIP with Bucket and HourGroup |
| rpt.EmployeeHoursVsBudgetMonth | Production / time | Budget Billable Hours, Over Under, Productivity measures |
| rpt.UnreleasedTimeWeek | Production / time | Unposted Time page |
| rpt.Billing | Billing & realization | The 3 Year Billing query; CAS BR/CBR measures |
| rpt.RealizationByPartnerMonth | Billing & realization | CAS vw_practice_summary |
| rpt.WipBalance | WIP balance | CAS WS / Recon measures |
| rpt.ClientEngagementNewBusiness + usp.Rpt_ClientGroupSummary @AsOfDate | Client lifecycle | NB vw_GroupSummary, GroupSummary_Final_ |
| rpt.ProjectBudgetVsActual, rpt.ProjectUnbudgetedHours, rpt.SkillVariance, rpt.ProjectCurrentStatus | Project management | CAS fact_budget_actuals, kanban_project_summary, fact_skill_variance, vw_project_current_status |
| rpt.CapacityWeekly + usp.Rpt_CapacityWeekly, usp.Rpt_ForecastCompliance | Capacity & forecast | CAS vw_capacity_weekly, vw_forecast_submission_compliance, fact_forecast_vs_actual |
| rpt.ArSummaryByClient | AR / collections | vpm9_AR_* (unused) and NB lifetime totals |
| usp.Rpt_BillingSummary @Year, @CutoffMonth; usp.Rpt_LostClients @Year, @CutoffMonth | Billing & lifecycle | 3 Year Billing pages 1-4 (YTD/PYTD, lost clients, seasonal gap) |

# 4. Decisions needed before building

These are the business-rule choices that the reports currently make differently. Each needs one answer, recorded in the sqlproj README, before the corresponding phase starts. Recommended defaults are shown; they match the draft DDL.

| # | Decision | Options | Recommended / owner |
| --- | --- | --- | --- |
| 1 | Canonical "Amount Invoiced" | WIP-derived (H, P rows on Wipdate) vs. Invoice table (InvAmount + InvAdjust on InvDate) | WIP-derived as primary (matches 3YB and CAS); Invoice exposed separately. Confirm after the section 6 tie-out. Jake + billing partner |
| 2 | Realization formula | 1 + adj / (bill - adj) (3YB) vs. BilledActual / BilledStandard (CAS) | Expose both; pick one for the named measure. Billing partner |
| 3 | Hours bucket rule | PTO = WType 1, 2, 4, 5; Other = 3; Marketing = 6; Billable = WType 0 and Wbillable 1 | Adopt as stated (the DAX HourGroup rule, extended). Confirm Sick/Holiday/Personal count as PTO. HR / ops |
| 4 | Week convention | Monday start (CAS, NB, all CAS SQL) vs. Sunday start (Annual/Timesheet DAX) | Monday firm-wide; dim.Date carries both during transition. Jake |
| 5 | Employee scope | Include inactive and terminated employees in dim.Employee | Yes, with IsActive / IsDeleted flags. Jake |
| 6 | Client PII | Exclude Engfedid, Engss1, Engss2, phone, address from the warehouse | Exclude. Confirm no downstream need. Jake |
| 7 | Skill tier and bill rates | Confirm the 21-row SkID map; identify which of Emprate1-25 is "standard" and which is "non-bill" | Jake to confirm from PM configuration; blocks dim.Employee completion |
| 8 | Fiscal year | Oct-Sep (CAS) firm-wide, or CAS only | Carry FiscalYear in dim.Date regardless. Finance |
| 9 | Where the warehouse lives | lgt_reporting on LGT-VMW2 (current) vs. schemas inside lgt | lgt_reporting, already in place. Done |
| 10 | Sqlproj conventions | Adopt the draft's ref/dim/fact/rpt/usp schemas and PascalCase names, or extend the current staging/dim/fact + snake_case scaffold | Adopt the draft conventions; rename the four existing tables now while they are empty. Eric + Jake, Phase 0 |

# 5. Phased work plan

Order matters: reference data and the calendar first, then the WIP fact with a billing tie-out, then reports in increasing order of complexity. No report is repointed until the numbers behind it have been reconciled against the current version for at least one closed year. Estimates are working hours and assume the two-machine workflow described in the sqlproj README (Eric edits on the laptop, Jake builds and publishes from the VM).

| Phase | Name | Work | Done when | Est. hours |
| --- | --- | --- | --- | --- |
| 0 | Reconcile the two designs | Merge the draft DDL into lgt-reporting-db under one convention (Decision 10). Rename dim_client, dim_client_group, dim_employee, fact_engagement; add ref, rpt, usp schemas; add ETL log table. Verify every source column name in the draft against lgt (types were inferred from the models, not the source). Record Decisions 1-10 in the README. | sqlproj builds clean; schema compare against lgt_reporting shows only intended changes | Eric 2-3, Jake 6-8 |
| 1 | Reference data and dimensions | Deploy ref.* and load from the hardcoded model tables (NAIC map, goals, skill tiers, eligibility, status sort, LOB groups, time types, partner exclusions). Deploy dim.Date. Deploy and load dim.Employee, dim.ClientEngagement, dim.ClientGroup, dim.Client, dim.SkillLevel, dim.ServiceCode, dim.Department, and the CAS project dims. Resolve the four open dim.Employee columns (Decision 7). | Row counts match source; every SkID maps to a rank (none = 99); every Engrelated resolves to a group label | Eric 3-4, Jake 12-16 |
| 2 | WIP fact and billing tie-out | Deploy fact.WipTransaction with the conformed columns in 3.3 and the incremental load on Wdstamp. Deploy fact.Invoice (deduped) and fact.ArTransaction. Run the tie-out in section 6 for one closed year and the current YTD. Resolve Decisions 1 and 2 with the results. | rpt.Billing totals equal 3 Year Billing [Billings], [Adj], [Hrs] and CAS BR Total Invoiced by partner and month for the test year, to the cent, or every difference is explained and accepted in writing | Eric 4-6, Jake 16-24 |
| 3 | Timesheet Review (retire Annual Review) | Deploy rpt.WipProduction, rpt.EmployeeHoursVsBudgetMonth, rpt.UnreleasedTimeWeek, fact.TimeEntryUnreleased, fact.EmployeeBudgetMonth. Rebuild Timesheet Review on the views: remove the 126/102-column imports, the 26 auto-date tables, the M/DAX bucket columns. Publish the Annual Review pages inside it and retire the separate model. | Staff Hours vs. Goal and Unposted Time match the current report for the last 8 weeks; refresh time and model size recorded before/after | Eric 2-3, Jake 10-14 |
| 4 | Rebuild 3 Year Billing | Rebuild on rpt.Billing plus usp.Rpt_BillingSummary and usp.Rpt_LostClients. Drop vpm9_*, Employee, SICCode, NAIC_Niche, and the partner-exclusion DAX column. Keep the CutoffMonth slicer as a parameter to the procedures. Optimize the Lost Clients / Seasonal Gap logic into SQL. | All five pages reproduce current values for the prior two years plus YTD; refresh no longer touches production | Eric 3-4, Jake 8-12 |
| 5 | Migrate CAS Management | Move the 26 native queries to the warehouse: dims already in place from Phase 1; deploy fact.ProjectBudgetLine, fact.ProjectStatusLog, fact.EmployeeSchedule, fact.EmployeeForecastWeek and the project/capacity views and procs. Replace GETDATE() windows with @AsOfDate parameters. Fix the SkDesc rank bug. Keep incremental refresh, now on fact.WipTransaction. | Each CAS page matches the current DEV report as of the same date; skill variance counts change only where the rank bug was corrected, and those changes are listed | Eric 6-8, Jake 24-32 |
| 6 | Migrate New Business Report | Rebuild on dim.ClientGroup, rpt.ClientEngagementNewBusiness, usp.Rpt_ClientGroupSummary, usp.Rpt_NewBusiness and ref.NicheGoal. Remove the DAX re-implementation (GroupSummary_Final_) and the embedded NicheTable. | New vs. expanded totals by niche and department match the current report for the current year; group labels reviewed by partners | Eric 3-4, Jake 10-14 |
| 7 | Cutover and operations | Schedule usp.Load_All as a SQL Agent job (nightly, with the WIP incremental); add ETL logging and a failure alert; remove production credentials from every published dataset; set up gateway/refresh on the warehouse only; document the runbook in the sqlproj README. | No published dataset references lgt-pm03; nightly load succeeds for five consecutive nights; Jake can rerun a load and republish a report without Eric | Eric 4-6, Jake 10-12 |

Total: roughly 28 to 40 hours for Eric and 95 to 130 hours for Jake. Phases 3, 4, and 6 are independent once Phase 2 is accepted and can be reordered if a report is needed sooner. Phase 5 is the largest and should not start until Phase 2 has been signed off, because every CAS billing measure depends on the same conformed columns.

## 5.1 Suggested sequence

- Phase 0 and 1 together in the first two working weeks. Nothing user-facing changes.

- Phase 2 as its own milestone with a written sign-off from the billing partner on the tie-out. This is the point where the firm agrees on what "billings" means.

- Phase 3 next because it is the simplest repoint and retires a duplicate model immediately.

- Phase 4 (3 Year Billing) as the first billing report on the new base, then Phase 6, then Phase 5.

- Phase 7 runs alongside from Phase 3 onward; the Agent job should exist before the first report goes live on the warehouse.

# 6. Billing tie-out test specification

The acceptance test for Phase 2. It is run once against a closed calendar year (recommended: 2025) and once against the current YTD, and rerun after every change to fact.WipTransaction.

### Test 1: WIP-derived billings by partner and month

- Query rpt.Billing grouped by PrimaryPartnerLastName and YearMonthNum: SUM(InvoicedAmount), SUM(WriteUpDownAmount), SUM(BilledHours).

- Export the same grain from the current 3 Year Billing report ([Billings], [Adj], [Hrs] by CPPLname and MonthStart).

- Expected: identical to the cent. Any difference is traced to a WIP row and explained (most likely causes: rows with Windicator D, rows with NULL Wipdate, or the partner exclusion list).

### Test 2: CAS BR Total Invoiced

- Same query, compared to CAS BR Total Invoiced by month and by client. CAS uses Wipdate through an inactive relationship, so the date basis should already agree.

### Test 3: Fees / production

- SUM(ProductionAmount) by WorkDate month vs. 3 Year Billing [Fee Amount] and CAS Gross WIP. CAS uses Wfee + Wexp without surcharge, so a known difference equal to SUM(Wsurchg) minus SUM(Wexp) is expected and documented; this is what Decision 2 resolves.

### Test 4: WIP-derived vs. Invoice table

- SUM(fact.WipTransaction.InvoicedAmount) by Cltnum and month vs. SUM(fact.Invoice.NetBilledAmount) by InvCltNumber and InvDate month. Report the variance by client. This quantifies Decision 1; it is not expected to be zero.

### Test 5: Hours buckets

- SUM(Hours) by HoursBucket and employee for the last 8 weeks vs. Timesheet Review Bucket and HourGroup. Differences appear only where the two old rules disagreed (WType 1, 4, 5 rows); list them for HR confirmation under Decision 3.

# 7. Risks and dependencies

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Source column names in the draft DDL were inferred from the models, not the lgt schema | Load procedures fail or silently map the wrong column | Phase 0 verifies every referenced column against INFORMATION_SCHEMA on lgt before any load runs |
| lgt_reporting is reachable only from the LGT-VMW2 RDP session | Eric cannot build, publish, or test directly; every cycle goes through Jake | Keep the GitHub sync discipline (Sync Changes at the start and end of every RDP session); batch changes per phase; Jake runs the tie-out queries and commits results to the repo |
| Two warehouse designs already diverge | Rework if more tables are added to the sqlproj before reconciling | Phase 0 is first and short; freeze the sqlproj to structure changes until it is done |
| Unresolved bill-rate and skill mappings (Decision 7) | dim.Employee ships with NULL rates; CAS realization and cost measures cannot be validated | Jake pulls the rate-tier configuration from PM; if unavailable, Phase 5 measures that depend on it are flagged as provisional |
| Partners disagree on the canonical billing definition (Decisions 1-2) | Phase 2 sign-off stalls; downstream phases wait | Present the Test 3 and Test 4 variances with dollar amounts; the decision is about which number to publish, not about rebuilding anything |
| Tax-ID and SSN columns exist in three published datasets today | Compliance exposure until those models are retired | Phases 3, 4, and 6 remove them; consider re-publishing the current models without those columns as an interim step |
| CAS custom kanban visual and 148 measures | Largest migration surface; regression risk | Migrate CAS last; measures are already SQL-backed so most changes are connection swaps; keep the DEV copy live until parity is signed off |

# Appendix A: Object mapping (current model to warehouse)

Every imported table in the five models and where it goes. "Drop" means the object is not carried forward.

| Model | Current table | Warehouse object | Note |
| --- | --- | --- | --- |
| 3 Year Billing | 3 Year Billing (native query) | rpt.Billing + usp.Rpt_BillingSummary | Conformed columns replace CASE expressions |
| 3 Year Billing | Clients, Department, SICCode | dim.ClientEngagement, dim.Department | SICCode description folded into dim.ClientEngagement |
| 3 Year Billing | Employee | Drop | Unused by visuals |
| 3 Year Billing | vpm9_AR_Invoices, vpm9_AR_Payments_by_Client, vpm9_AR_Payments_by_Master, vpm9_main_billing | Drop (rpt.ArSummaryByClient if AR is needed) | Unused by visuals |
| 3 Year Billing | NAIC_Niche, CutoffMonth, Date | ref.NaicNiche, procedure parameter, dim.Date |  |
| Annual / Timesheet | Fact_WIP | rpt.WipProduction | Bucket / HourGroup replaced by HoursBucket |
| Annual / Timesheet | Fact_TimeEntry | rpt.UnreleasedTimeWeek | Only unreleased rows needed |
| Annual / Timesheet | Fact_EmpBudHRS, Fact_EmpCltBudget | fact.EmployeeBudgetMonth, fact.EmployeeSchedule |  |
| Annual / Timesheet | Dim_Clients, Dim_Employee, Dim_Department, Fact_SkillLevel, ServiceCodes | dim.ClientEngagement, dim.Employee, dim.Department, dim.SkillLevel, dim.ServiceCode | Name format Last, First available as NameLastFirst |
| Annual / Timesheet | DimDate + 26 LocalDateTable_* | dim.Date | Disable auto date/time in the model |
| Annual / Timesheet | LastRefresh | ETL log table (Phase 7) |  |
| CAS Management | dim_client, dim_employee, dim_department, dim_service_code, dim_lob, dim_entity_type, dim_work_type, dim_project, dim_project_type, dim_project_position, dim_tracking_status | dim.* (same names in PascalCase) | dim_employee no longer filters Empstatus = A |
| CAS Management | dim_date, dim_skill_rank, SkillRoleEligibility, StatusSortOrder, Project Health Filter | dim.Date, ref.SkillLevelTier, ref.PositionSkillEligibility, ref.ProjectStatusSort, ref.Setting |  |
| CAS Management | fact_wip | fact.WipTransaction / rpt.WipBalance / rpt.Billing | Incremental refresh retained |
| CAS Management | fact_invoice | fact.Invoice | Deduped by InvNumber |
| CAS Management | fact_budget_lines, fact_budget_actuals, fact_project_status_log, fact_skill_variance, kanban_project_summary | fact.ProjectBudgetLine, rpt.ProjectBudgetVsActual, fact.ProjectStatusLog, rpt.SkillVariance, rpt.ProjectCurrentStatus |  |
| CAS Management | fact_schedule, fact_capacity, fact_forecast, fact_forecast_vs_actual, vw_capacity_weekly, vw_forecast_submission_compliance | fact.EmployeeSchedule, fact.EmployeeForecastWeek, rpt.CapacityWeekly, usp.Rpt_CapacityWeekly, usp.Rpt_ForecastCompliance | Rolling windows become @AsOfDate / @WeeksBack |
| CAS Management | vw_practice_summary, vw_project_current_status, vw_skill_violation_summary | rpt.RealizationByPartnerMonth, rpt.ProjectCurrentStatus, usp.Rpt_SkillViolationSummary |  |
| CAS Management | Employee Selector, Employee Filter Mode | Keep in model | UI helper tables |
| New Business | vw_GroupSummary, GroupSummary_Final_, ClientsMarActDate | dim.ClientGroup + usp.Rpt_ClientGroupSummary | DAX re-implementation dropped |
| New Business | Clients, Employee, Department, LineOfBusiness | dim.ClientEngagement, dim.Employee, dim.Department, dim.LineOfBusiness |  |
| New Business | NicheTable, NicheGoals, ManualGroupLabel | ref.NaicNiche, ref.NicheGoal, ref.ClientGroupLabelOverride |  |
| New Business | Date + 25 LocalDateTable_* | dim.Date |  |
| sqlproj (current) | staging.Clients, staging.Staff | Keep as staging mirrors; widen to the column list in section 3.1 |  |
| sqlproj (current) | dim.dim_client, dim.dim_client_group, dim.dim_employee, fact.fact_engagement | dim.Client, dim.ClientGroup, dim.Employee, dim.ClientEngagement | Rename in Phase 0 while empty |

# Appendix B: Source-table quirks to preserve

Findings from reading the current models that the load procedures must respect. These are easy to lose in a rebuild.

- WIP, EmpBudHRS, EmpCltBudget, CltBudget have no Deleted column; Clients, Employee, CltDue, EmpForecast, LineOfBusiness, ServiceCodes do.

- Clients.Marnew is unreliable; derive "new client" from ROW_NUMBER() over Maractdate within the group.

- Invoice joins to Clients on Cltnum only (InvCltNumber has no engagement suffix) and fans out; dedupe by InvNumber before joining.

- AcctsRec finance charges (ARType 3) store the amount in ARFin; ARAmt is zero. ARType 4 is a payment. Filter ARStatus = P and ARVoid = 0.

- Engstatus: 0 Active, 1 Inactive, 2 Hold, 3 Active Prospect, 4 Inactive Prospect.

- Windicator: W unbilled WIP, H billed history, P progress bill, D deleted/void (exclude).

- WType / SCType: 0 Regular, 1 Sick, 2 Vacation, 3 CPE, 4 Holiday, 5 Personal, 6 Marketing.

- Engwork (WorkEntity Type = W) drives CAS line of business, not EngLOB.

- Partner attribution comes from three different places today: Clients.CPPLname (3YB, Timesheet), Engcltptr to Employee (CAS, NB), and CRPnum to Employee.Empnum for originator (NB). dim.ClientEngagement carries all three resolved to employee IDs.